## Slide 1: Chapter 13: Project Stakeholder Management
Information Technology Project Management, Ninth Edition
Note: See the text itself for full citations

## Slide 2: Learning Objectives
Explain the importance of project stakeholder management throughout the life of a project
Discuss the process of identifying stakeholders, how to create a stakeholder register, and how to perform a stakeholder analysis
Describe the contents of a stakeholder engagement plan
Describe the process of managing stakeholder engagement
Explain methods for monitoring stakeholder engagement
Discuss types of software available to assist in project stakeholder management
Discuss considerations for agile/adaptive environments

## Slide 3: Importance of Project Stakeholder Management (1 of 4)
Because stakeholder management is so important to project success, the Project Management Institute decided to create an entire knowledge area devoted to it in 2013
  The purpose of project stakeholder management is to identify all people or organizations affected by a project, to analyze stakeholder expectations, and to effectively engage stakeholders

## Slide 4: Importance of Project Stakeholder Management (2 of 4)
Projects often cause changes in organizations, and some people may lose their jobs when a project is completed
  Project managers might be viewed as enemies
  By contrast, they could be viewed as allies if they lead a project that helps increase profits, produce new jobs, or increase pay for certain stakeholders
In any case, project managers must learn to identify, understand, and work with a variety of stakeholders

## Slide 5: What Went Wrong?
Changing the way work is done can send a shock wave through an organization, leaving many people afraid and even thinking about ways to stop or sabotage a project
  Donald White, founder and program manager at Defense Systems Leaders in Washington, D.C., described situations that can lead to project sabotage:
    Buy-in blues
    Short-term profits
    Overachieving
    Lack of respect

## Slide 6: Importance of Project Stakeholder Management (3 of 4)
Project stakeholder management processes
  Identifying stakeholders: identifying everyone involved in the project or affected by it, and determining the best ways to manage relationships with them
  Planning stakeholder management: determining strategies to effectively engage stakeholders
  Managing stakeholder engagement: communicating and working with project stakeholders to satisfy their needs and expectations, resolving issues, and fostering engagement in project decisions and activities
  Monitoring stakeholder engagement: monitoring stakeholder relationships and adjusting plans and strategies for engaging stakeholders as needed

## Slide 7: Importance of Project Stakeholder Management (4 of 4)

## Slide 8: Identifying Stakeholders (1 of 7)
Internal project stakeholders generally include the project sponsor, project team, support staff, and internal customers for the project
  Other internal stakeholders include top management, other functional managers, and other project managers because organizations have limited resources
External project stakeholders include the project’s customers (if they are external to the organization), competitors, suppliers, and other external groups that are potentially involved in the project or affected by it, such as government officials and concerned citizens

## Slide 9: Identifying Stakeholders (2 of 7)
Peter Gilliland, a project management tutor and skills coach in the United Kingdom, offers an even more detailed list of potential stakeholders for a project, including:
  Program director and manager
  Project manager and family
  Sponsors
  Customers
  Labor unions
  Potential customers
  Competitors
It is also necessary to focus on stakeholders with the most direct ties to a project
  Example: only key suppliers

## Slide 10: Identifying Stakeholders (3 of 7)
A stakeholder register includes basic information on stakeholders
  Identification information: stakeholders’ names, positions, locations, roles in the project, and contact information
  Assessment information: stakeholders’ major requirements and expectations, potential influences, and phases of the project in which stakeholders have the most interest
  Stakeholder classification: is the stakeholder internal or external to the organization? Is the stakeholder a supporter of the project or resistant to it?

## Slide 11: Identifying Stakeholders (4 of 7)
Name | Position | Internal/ External | Project Role | Contact Information
Stephen | VP of Operations | Internal | Project sponsor | stephen@globaloil.com
Betsy | CFO | Internal | Senior manager, approves funds | betsy@globaloil.com
Chien | CIO | Internal | Senior manager, PM’s boss | chien@globaloil.com
Ryan | IT analyst | Internal | Team member | ryan@globaloil.com
Lori | Director, Accounting | Internal | Senior manager | lori@globaloil.com
Sanjay | Director, Refineries | Internal | Senior manager of largest refinery | sanjay@globaloil.com
Debra | Consultant | External | Project manager | debra@gmail.com
Suppliers | Suppliers | External | Supply software | suppliers@gmail.com
Table 13-1 Sample stakeholder register

## Slide 12: Identifying Stakeholders (5 of 7)
After identifying key project stakeholders, you can use different classification models to determine an approach for managing stakeholder relationships
  A power/interest grid can be used to group stakeholders based on their level of authority (power) and their level of concern (interest) for project outcomes

## Slide 13: Identifying Stakeholders (6 of 7)

## Slide 14: Identifying Stakeholders (7 of 7)
Stakeholder engagement levels
  Unaware: unaware of the project and its potential impacts on them
  Resistant: aware of the project yet resistant to change
  Neutral: aware of the project yet neither supportive nor resistant
  Supportive: aware of the project and supportive of change
  Leading: aware of the project and its potential impacts and actively engaged in helping it succeed

## Slide 15: What Went Right?
Instead of just saying “no” when your project sponsor asks for something unreasonable, it is better to explain what is wrong with the request and then present a realistic way to solve the problem at hand
  Christa Ferguson, a PMP® and independent program manager in San Francisco, described how she handled a request from a project sponsor to deliver a new tablet device in two months when she knew she would need more time
    Based on her experience, she knew the RFQ for the effort alone would take almost a month
    Christa quickly researched the facts to propose a realistic delivery schedule
    The project sponsor reset expectations once he learned what it took to produce the tablets

## Slide 16: Planning Stakeholder Management (1 of 2)
After identifying and analyzing stakeholders, project teams should develop a plan for management them
  May be formal or informal, based on the needs of the project
The stakeholder management plan can include:
  Current and desired engagement levels
  Interrelationships between stakeholders
  Communication requirements
  Potential management strategies for each stakeholders
  Methods for updating the stakeholder management plan

## Slide 17: Planning Stakeholder Management (2 of 2)
Because a stakeholder management plan often includes sensitive information, it should not be part of the official project documents, which are normally available for all stakeholders to review
  In many cases, only project managers and a few other team members should prepare the stakeholder management plan
  Parts of the stakeholder management plan are not written down, and if they are, distribution is strictly limited

## Slide 18: Managing Stakeholder Engagement (1 of 4)
Project success is often measured in terms of customer/sponsor satisfaction
  Project sponsors often rank scope, time, and cost goals in order of importance and provide guidelines on how to balance the triple constraint
    This ranking can be shown in an expectations management matrix to help clarify expectations

## Slide 19: Managing Stakeholder Engagement (2 of 4)
Measure of Success | Priority | Expectations | Guidelines
Scope | 1 | The scope statement clearly defines mandatory requirements and optional requirements. | Focus on meeting mandatory requirements before considering optional ones. In this case, following corporate IT standards is optional.
Time | 1 | There is little give in the project completion date. The schedule is very realistic. | The project sponsor must be alerted if any issues might affect meeting schedule goals.
Cost | 3 | This project is crucial to the organization. If you can clearly justify the need for more funds, they can be made available. | There are strict rules for project expenditures and escalation procedures. Cost is very important, but it takes a back seat to meeting schedule and then scope goals.
Technology/ standards | 2 | There are several potential solutions available, but only one that meets all of the sponsor’s technical requirements, especially for accounting. | While corporate IT standards are important, an exception makes sense in this case.
Table 13-3 Expectations management matrix

## Slide 20: Managing Stakeholder Engagement (3 of 4)
Understanding the stakeholders’ expectations can help in managing issues
  Issues should be documented in an issue log, a tool used to document, monitor, and track issues that need resolution
  Unresolved issues can be a major source of conflict and result in stakeholder expectations not being met
  Issue logs can address other knowledge areas as well

## Slide 21: Managing Stakeholder Engagement (4 of 4)
Issue # | Description | Impact | Date Reported | Reported By | Assigned to | Priority (H/M/L) | Due Date | Status | Comments
1 | Need requirements categorized as mandatory and optional | Cannot do much without it | Feb. 4 | Ryan | Stephen | H | Feb. 8 | Closed | Requirements clearly labeled
2 | Need shorter list of potential suppliers —no more than 10 | Will delay evaluation without it | Feb. 6 | Debra | Ryan | H | Feb. 12 | Open | Almost finished; needed requirements categorized first
Etc. |  |  |  |  |  |  |  |  | 
Table 13-4 Sample issue log

## Slide 22: Best Practice
Project managers are often faced with challenges, especially in managing stakeholders
  Sometimes they simply cannot meet requests from important stakeholders
Suggestions for handling these situations
  Be clear from the start
  Explain the consequences
  Have a contingency plan
  Avoid surprises
  Take a stand

## Slide 23: Monitoring Stakeholder Engagement (1 of 2)
You cannot control stakeholders, but you can control their level of engagement
  Engagement involves a dialogue in which people seek understanding and solutions to issues of mutual concern
Many teachers are familiar with various techniques for engaging students
  It is important to set the proper tone at the start of a class or project

## Slide 24: Monitoring Stakeholder Engagement (2 of 2)
If a teacher does nothing but lecture on the first day of class or criticizes the first person who offers a comment, students will quickly decide that their best strategy is to keep quiet and maybe not even attend the class
  On the other hand, if the teacher uses a lot of activities to get all participants to speak or use technology to participate, they will expect to be active participants in future classes

## Slide 25: Media Snapshot
Many students today like to interact via text messages
  Ellen DeGeneres, a popular comedian with her own television show, likes to poke fun at text messages in a segment based on amusing errors caused by cell phone auto-correct features
  In addition to watching out for auto-correct errors when messaging, users must also be careful who they reply to and what they say in reply

## Slide 26: Using Software to Assist in Project Stakeholder Management (1 of 2)
Productivity software like word processors, spreadsheets, and presentation software can aid in creating various documents related to stakeholder management
Communications software like e-mail, blogs, websites, texts, and tweets can aid in stakeholder communications
Collaboration tools like Google docs, wikis, and virtual meeting software can also promote stakeholder engagement in projects

## Slide 27: Using Software to Assist in Project Stakeholder Management (2 of 2)
Social media can also help engage stakeholders
  LinkedIn has thousands of groups for project management professionals
  Some project management software includes functionality like Facebook’s to encourage relationship building on projects, like giving high fives for a job well done
It is crucial that project managers and their teams focus on monitoring stakeholder engagement to meet their needs and expectations, not to show off the latest technology
  A lot of stakeholder engagement requires old-fashioned techniques like talking to someone

## Slide 28: Global Issues
Not all software implementations go well, and managing stakeholders is a major challenge
  The U.K. government scrapped its £11.4 billion national healthcare IT initiative in September 2011 after it failed to deliver the promised benefits
    Unfortunately, this project was just one in a series of high-profile failures in the U.K.
  In response, the government decided to send its project managers back to school
    They partnered with the University of Oxford and the Deloitte consulting firm to establish the Major Projects Leadership Academy in Oxford, England
    Currently, 300 people are categorized as major project leaders in the British government
    The academy enrolls over 100 major project leaders each year

## Slide 29: Considerations For Agile/Adaptive Environments
It is important to understand and involve key stakeholders on all projects
  The nature of agile/adaptive projects, however, does often require more stakeholder involvement and faster decision making
  Product owners create the backlog for each iteration, thereby ensuring that their priorities are clear
Posting project artifacts in a public space can be done on agile and non-agile projects
  Based on the sensitivity of the information and type of project

## Slide 30: Chapter Summary
Managing stakeholders is now the tenth knowledge area in the PMBOK® Guide
  Processes include:
    Identifying stakeholders
    Planning stakeholder engagement
    Managing stakeholder engagement
    Monitoring stakeholder engagement
  Several types of software can assist in project stakeholder management
    Social media can also help in developing relationships with stakeholders